## Overview
Event Planning Checklist
5 Phases ¦ 70 Tasks ¦ Event XYZ
Phase | Period | Tasks | Completed
Phase 1 – Strategy | 12–18 months before | 13 | 0
Phase 2 – Planning | 6–12 months before | 15 | 0
Phase 3 – Preparation | 3–6 months before | 15 | 0
Phase 4 – Execution | On the event day | 14 | 0
Phase 5 – Follow-up | Within 2 weeks | 13 | 0
TOTAL |  | 70 | 0
0 of 70 tasks completed (0%)
Legend – Categories
Strategy |  | Budget
Logistics |  | Team
Marketing |  | Technology
Programme |  | Risk
Analysis

## 🎯 Strategy
Phase 1 – Strategy
Period: 12–18 months before
No. | Task | Status | Category | Notes / Responsible
1 | Define event format (conference, workshop, staff event) | Pending | Strategy
2 | Formulate event objectives clearly | Pending | Strategy
3 | Define KPIs for success | Pending | Strategy
4 | Identify target audience | Pending | Strategy
5 | Set budget (rough planning) | Pending | Budget
6 | Choose event date | Pending | Logistics
7 | Check competing events (use AI prompt) | Pending | Logistics
8 | Assemble internal planning team | Pending | Team
9 | Distribute responsibilities | Pending | Team
10 | Determine required contact list size | Pending | Marketing
11 | Evaluate event venue (initial shortlist) | Pending | Logistics
12 | Conduct risk analysis | Pending | Risk
13 | Outline contingency plan (Plan B) for critical areas | Pending | Risk
0 of 13 tasks completed |  | 0/13

## 📐 Planning
Phase 2 – Planning
Period: 6–12 months before
No. | Task | Status | Category | Notes / Responsible
1 | Book venue definitively & sign contract | Pending | Logistics
2 | Invite & confirm speakers / presenters | Pending | Programme
3 | Develop programme & agenda logic | Pending | Programme
4 | Finalise event concept & key idea | Pending | Strategy
5 | Request & obtain catering quotes | Pending | Logistics
6 | Plan sound & AV technology | Pending | Technology
7 | Select & commission service providers | Pending | Logistics
8 | Sign contracts with all service providers | Pending | Logistics
9 | Build & launch event website | Pending | Marketing
10 | Set up registration logic & sign-up form | Pending | Technology
11 | Define early-bird ticket strategy | Pending | Marketing
12 | Create communication plan & timeline | Pending | Marketing
13 | Define social media strategy | Pending | Marketing
14 | Develop detailed budget | Pending | Budget
15 | Commission event agency (if desired) | Pending | Logistics
0 of 15 tasks completed |  | 0/15

## ✅ Preparation
Phase 3 – Preparation
Period: 3–6 months before
No. | Task | Status | Category | Notes / Responsible
1 | Send out first invitations | Pending | Marketing
2 | Plan & send reminder emails | Pending | Marketing
3 | Track registration numbers daily | Pending | Marketing
4 | Configure event technology (e.g. Oniva) | Pending | Technology
5 | Set up check-in system & QR codes | Pending | Technology
6 | Create run-of-show / event schedule | Pending | Logistics
7 | Plan signage & wayfinding | Pending | Logistics
8 | Produce materials & print items | Pending | Logistics
9 | Prepare briefings for all parties involved | Pending | Team
10 | Optimise costs (sharing, reuse of materials) | Pending | Budget
11 | Finalise contingency plan (Plan B) | Pending | Risk
12 | Plan & conduct technical rehearsal | Pending | Technology
13 | Finalise catering menu & dietary requirements | Pending | Logistics
14 | Clean up & finalise participant list | Pending | Logistics
15 | Issue press release / PR measures (if relevant) | Pending | Marketing
0 of 15 tasks completed |  | 0/15

## 🎪 Execution
Phase 4 – Execution
Period: On the event day
No. | Task | Status | Category | Notes / Responsible
1 | Start setup early (allow +30% time buffer) | Pending | Logistics
2 | Tech check: sound, lighting, projector, Wi-Fi | Pending | Technology
3 | Catering setup & quality control | Pending | Logistics
4 | Appoint team coordinator (coordination only) | Pending | Team
5 | Brief all on-site helpers | Pending | Team
6 | Manage entrance & check-in smoothly | Pending | Logistics
7 | Follow & adapt event schedule as needed | Pending | Programme
8 | Actively take on host role | Pending | Programme
9 | Coordinate live documentation (photos, video) | Pending | Marketing
10 | Post on social media in real time | Pending | Marketing
11 | Handle unexpected issues calmly | Pending | Risk
12 | Actively support & connect attendees | Pending | Programme
13 | Coordinate teardown | Pending | Logistics
14 | Collect inventory & materials | Pending | Logistics
0 of 14 tasks completed |  | 0/14

## 📊 Follow-up
Phase 5 – Follow-up
Period: Within 2 weeks
No. | Task | Status | Category | Notes / Responsible
1 | Send feedback survey on the evening / next day | Pending | Analysis
2 | Evaluate feedback & measure response rate | Pending | Analysis
3 | Analyse KPIs (attendance, NPS, registrations) | Pending | Analysis
4 | Send thank-you emails to all participants | Pending | Marketing
5 | Check & pay invoices | Pending | Budget
6 | Produce budget final report (target vs. actual) | Pending | Budget
7 | Create event report | Pending | Analysis
8 | Document learnings & improvements | Pending | Analysis
9 | Rate service providers & give feedback | Pending | Logistics
10 | Hold team debrief | Pending | Team
11 | Prepare highlight content (blog, LinkedIn …) | Pending | Marketing
12 | Qualify & hand over leads from the event | Pending | Marketing
13 | Lay groundwork for the next event | Pending | Strategy
0 of 13 tasks completed |  | 0/13